## Sheet1
ToppersLectureNotes.com
Index | Activities | Starting Date | Duration | Gantt Chart
1 | Find out the requirement of Society | 2018-01-01 | 15 days
2 | Requirement gathering of our domain | 2018-01-16 | 10 days
3 | Requirement analysis | 2018-01-27 | 4 days
4 | Risk Assessment | 2018-02-01 | 5 days
5 | Planning task management | 2018-02-06 | 6 days
6 | Create Gannt Chart | 2018-02-12 | 2 days
7 | Create Traceability matrix | 2018-02-14 | 1 day
8 | RMMM Plan | 2018-02-15 | 1 day
9 | Design WireFrame | 2018-02-16 | 3 days
10 | Design App Home Screen | 2018-02-19 | 6 days
11 | Design Inner App Screen | 2018-02-25 | 12 days
12 | Implementation or coding | 2018-03-09 | 25 days
13 | Testing | 2018-04-04 | 6 days
14 | Deployment | 2018-04-10 | 1 day